## Transition Plan
Welcome! Use this project plan as a foundation for your rollout of visit verification. Refer to the transition guide for a more detailed description of each task. Use the "Start" and "End" columns to create your task timeline. Use the 'Status' column to track progress.
PLANNING
Step | Task | Details | Start | End | Effort (hrs) | Assignee | Status | Notes
1 | Initial communication | Send an internal communication to impacted staff about upcoming change and benefits of moving to visit verification (refer to guide for template) |  |  | 0.5 | Department Manager | Not Started
| Project kick off | Communicate project plan and timelines |  |  | 1 | Department Manager | Not Started
| Assign resources | Designate one or more individuals to own rollout activities |  |  | 0.5 | Department Manager | Not Started
| UAT environment refresh | If applicable, submit a request to have your UAT environment refreshed with a copy of Production data |  |  | 0 | AlayaCare | Not Started
2 | Bill code and pay code rules | Determine how you want quantities for bill codes and pay codes to be calculated for visits |  |  | 2 | Finance Team | Not Started
3 | Reasons and resolution vs acknowledgement | Determine whether you want to use reasons and resolutions for "In Violation" visits, or only acknowledgements |  |  | 0.5 | Coordination Team or Supervisors | Not Started
| Reasons and resolution values | Determine what reasons and corresponding resolutions you want |  |  | 3 | Coordination Team or Supervisors | Not Started
4 | Rule sets | Determine what visit verification rules are required and whether they apply at branch, payor, or service code levels |  |  | 8 | Coordination Team or Supervisors | Not Started
CONFIGURATION & TESTING
Step | Task | Details | Start | End | Effort (hrs) | Assignee | Status | Notes
5 | Setup bill code and pay code rules | Setup bill and pay code rules in test environment |  |  | 2 | Finance Team or Coordination Team or Supervisors | Not Started
6 | Setup reasons and resolutions | Setup reasons and resolutions in test environment |  |  | 2 | Finance Team or Coordination Team or Supervisors | Not Started
| Configure associations | Associate resolutions to reasons in test environment |  |  | 1 | Finance Team or Coordination Team or Supervisors | Not Started
7 | Setup rules sets | Setup rule sets in test environment |  |  | 3 | Finance Team or Coordination Team or Supervisors | Not Started
8 | Data cleanup | Clear historical "Not Approved" visits |  |  | 0.5 | Finance Team or Coordination Team or Supervisors | Not Started
9 | Validate setup | Complete workflows with testing data and update configuration as needed |  |  | 12 | Finance Team or Coordination Team or Supervisors | Not Started
TRAINING
Step | Task | Details | Start | End | Effort (hrs) | Assignee | Status | Notes
10 | Documentation | Update internal training and process documentation to include visit verification workflows |  |  | 2 | Department Manager or Supervisors | Not Started
11 | Staff onboarding | Ask applicable staff to review Zendesk articles and videos, and play in test environment |  |  | 4 | Finance Team or Coordination Team or Supervisors | Not Started
PRODUCTION LAUNCH
Step | Task | Details | Start | End | Effort (hrs) | Assignee | Status | Notes
12 | Enable configuration menus | Request to have the visit verification configuration pages enabled (refer to guide for template) |  |  | 0 | AlayaCare | Not Started
| Setup bill code and pay code rules | Setup bill and pay code rules in Production environment |  |  | 2 | Finance Team or Coordination Team or Supervisors | Not Started
| Setup reasons and resolutions | Setup reasons and resolutions in Production environment |  |  | 2 | Finance Team or Coordination Team or Supervisors | Not Started
| Configure associations | Associate resolutions to reasons in Production environment |  |  | 1 | Finance Team or Coordination Team or Supervisors | Not Started
| Setup rules sets | Setup rule sets in Production environment |  |  | 3 | Finance Team or Coordination Team or Supervisors | Not Started
| Data cleanup | Clear historical "Not Approved" visits |  |  | 0.5 | Finance Team or Coordination Team or Supervisors | Not Started
13 | Readiness check | Complete readines checklist and confirm team is ready to transition (refer to guide for template) |  |  | 2 | Department Manager or Supervisors | Not Started
| Enable feature | Request to have the visit verification feature enabled (refer to guide for template) |  |  | 0 | AlayaCare | Not Started
CONGRATULATIONS, YOU'VE SUCCESSFULLY LAUNCHED VISIT VERIFICATION!